## Logframe
Logframe
Project Title: | Telehealth Services for Myanmar
Project Manager: | Dr. Ulrich Kuch, Goethe University Frankfurt
Project Number: |  | Term of Project:
Indicators
| Description | Indicators | Comments / Assumptions
Goal | To improve health care access and quality in conflict-affected areas of Myanmar through telemedicine and capacity-building initiatives
Outcome | Enhanced healthcare delivery and provider capabiities in Ethnic Health Organizations (EHO) in the conflict-affected areas of Myanmar | 9,000 consultations conducted via moblie clinics by the end of 2027 1,800 specialist consultations conducted via tele-touring by the end of 2027 | From a total of 360 mobile clinic trips, 25 patients per mobile visit for primary health care and 5 patients per mobile visit for specialist health care will be needed to achieve these numbers
Output 1 | Tele-touring telemedicine services implemented | 1.1 A total of 360 tele-touring visits conducted in the 3 EHO coverage areas at the end of 2027 1.2 A total of 10,800 consultations conducted in the 3 EHO coverage areas through mobile clinics at the end of 2027 | 2 mobile teams from each EHO will conduct mobile clinics 2 times per month starting from the second semester of year 1. From which, they will refer and let consult directly with the specialist teams from TLKM through telemedicine
Activity 1.1 | Mapping and selection of mobile clinic areas under each EHO
Activity 1.2 | Assess and set up telemedicine infrastructure such as smart-phones, possible internet connnectivity and alternative sources for electricity
Activity 1.3 | Implement and manage tele-touring telemedicine services
Output 2 | MHPSS and data security training delivered | 2.1 Baseline MHPSS training conducted in all 3 EHO coverage areas 2.2 A total of 60 health care providers attended MHPSS training 2.3 A total of 3 data security training sessions conducted in all 3 EHO coverage areas 2.4 A total of 60 participants attended data security training | 2.1 MHPSS training to health care providers at year 1 (20 heatlh care providers from each EHO will attend the training) 2.3 Data security training will be conducted once a year for each of the 3 EHO targeting both health care providers and relevant staff in the organization
Activity 2.1 | Creating training materials
Activity 2.2 | Develop and deliver MHPSS and data security training
Activity 2.3 | Evaluate post-training assessment
Output 3 | MHPSS coordination workshop conducted | 3.1 A total of 180 MHPSS related health promotion sessions conducted at the time of mobile clinics 3.2 A total of 2 MHPSS coordination workshops conducted in 2026 and 2027 in all 3 EHO coverage areas | 3.1 Health care providers will provide MHPSS-related health promotion sessions at the time of mobile clinics once a month 3.2 MHPSS coordination workshop will be conducted between TLKM and respective providers in year 2 and year 3 by reviewing the needs and evaluating the way forward
Activity 3.1 | Plan for MHPSS coordination channel between TLKM and health care providers of EHOs
Activity 3.2 | Develop MHPSS working group between TLKM and health care providers of EHOs
Activity 3.3 | Conduct MHPSS coordination workshop in year 2 and year 3
Output 4 | Health promotion content developed and disseminated in ethnic languages | 4.1 Number of health promotion materials developed (12 new materials per year, totaling 36 by the end of year 3, in 3 major regional/local languages and Burmese language) | Each of the 3 participating EHOs serves multiple ethnic groups in their service areas and important health promotion topics will be developed and shared with the respective EHOs
Activity 3.1 | Develop health promotion materials in major regional/local languages and Burmese language
Activity 3.2 | Share those contents on the Facebook and/or YouTube channels of TLKM
Activity 3.3 | Share those health promotion messages with the respective EHOs